## POC Brief
POC Functional Requirements — Supplementary Document Graph Accuracy Pipeline
For an existing document/manual support system. Original diagrams are included as indicative logical flows, not final implementation architecture.
Area | Requirement Summary | Delivery Note
Objective | Build a supplementary accuracy-improvement pipeline that extracts, validates, and organises document knowledge into a graph/vector layer so the existing system can answer complex technical questions with greater accuracy. | Reuse existing capabilities where they are fit for purpose; upgrade or supplement where accuracy, traceability, security, or performance gaps exist.
Existing system assumption | The POC should not assume a full rebuild. It should integrate with the current application, user interface, document store, query flow, and support processes where practical. | Development firm to identify integration points, dependencies, and suitable upgrade paths.
Target use case | Technical manuals containing wiring diagrams, images, tables, and step-by-step instructions. | Accuracy is the primary success measure: exact ordered steps, diagram understanding, and end-user confidence.
Business schema | Create a business-friendly schema over the graph so objects and relationships make sense to non-technical users. | Example graph path: Product → Fault → Component → Wiring Diagram → Procedure → Step 1…n.
Response traceability | Answers must link back to the graph logical flow and show source pages, sections, diagram/image assets, and graph nodes used. | Responses from tools should be structured for reuse by the existing system.
Platform delivery | Deliver in line with common cloud-platform patterns, preferably AWS-native or AWS-compatible services where suitable. | Object storage, managed databases, graph/vector storage, container/serverless compute, logging, monitoring, IAM/SSO, encryption, and auditability should be considered.
Key POC Outcomes
1 | A user can upload/process a sample technical manual and inspect extracted text, images, diagrams, objects, relationships, and confidence levels.
2 | A business-friendly graph schema is created and used to make graph objects understandable to business users.
3 | Responses return exact steps in the correct order, with relevant warnings, prerequisites, tools, parts, and diagram references.
4 | Graph pages can show stored images/diagrams in popups for later referencing.
5 | Fast responses are supported using caching where appropriate, without hiding uncertainty or weak evidence.
6 | Role-based access, document security, auditability, and upgrade paths are documented.

## Requirements
Functional Requirements
Concise POC requirements for a supplementary pipeline that improves the accuracy of an existing system.
ID | Capability | Functional Requirement | Existing / Upgrade Note | Acceptance Evidence | Priority
FR-01 | Existing system integration | Map the current application, document storage, user flows, and query tools. Reuse what already exists and supplement only where the current system is not accurate, traceable, fast, or secure enough. | Where a capability exists, integrate. Where it is unsuitable, propose a lightweight POC upgrade and a production upgrade path. | Integration map and component responsibility matrix. | Must
FR-02 | Document ingestion & storage | Support upload/import of technical manuals, with POC focus on PDF. Store original documents and derived artefacts in object storage. | Use existing upload/storage where suitable; otherwise use AWS S3 or compatible storage pattern. | Uploaded manual can be stored, tracked, and processed. | Must
FR-03 | PDF extraction | Extract per-page text blocks, tables, images, and diagram candidates. Preserve page/section references and coordinates where practical. | Reuse current extraction if it preserves enough structure; upgrade if it loses step order or diagram context. | Text, image, and page metadata are visible for a sample manual. | Must
FR-04 | Diagram and image asset handling | Store technical diagrams, wiring images, and extracted image assets as first-class references linked to pages, graph nodes, and response evidence. | Images should be retained for graph page popups and answer-level evidence. | Graph node can open a popup showing the relevant wiring diagram/image. | Must
FR-05 | Document classification & context | Classify document type and infer relevant industry/sector/context where possible. | Use existing metadata if available; supplement with heuristic/AI classification if required. | Manual is classified with visible confidence and context metadata. | Should
FR-06 | Business-friendly graph schema | Create a schema that translates extracted technical content into business-readable objects and relationships, e.g. Product, Manual, Component, Connector, Circuit, Fault, Procedure, Step, Warning, Tool, Part, Diagram, Evidence. | This schema sits on top of the graph so business users can understand and navigate it. | Schema dictionary and sample graph path are available in the POC. | Must
FR-07 | Knowledge extraction | Run one or more extraction passes to identify entities, relationships, procedures, prerequisites, warnings, parts, tools, and diagram/component links. | Low-confidence results should trigger validation or another extraction pass. | Extracted objects and relationships can be reviewed before graph commit. | Must
FR-08 | Validation workflow | Provide a review/edit step for extracted knowledge, especially low-confidence procedures, diagrams, and component relationships. | Use existing admin/review screens where possible; otherwise provide a lightweight POC interface. | Reviewer can amend extracted objects and approve them into the graph. | Must
FR-09 | Graph/vector storage | Build and store a graph family with vector search support, cached rebuilds, and traceable links back to source pages/assets. | Use a suitable graph/vector database aligned to the common platform, e.g. AWS-compatible managed services where appropriate. | Graph and vector lookups return relevant nodes and evidence. | Must
FR-10 | Query response contract | Tool responses must include answer, ordered steps, evidence, graph path, confidence, source references, image references, and any review/escalation flags. | Structured output should be reusable by the existing system and UI. | Sample query returns a structured response with graph trace and source links. | Must
FR-11 | Graph-linked answer UX | Every answer should link back to a business-friendly graph logical flow and show the source images/diagrams used, preferably through graph page popups. | UI can reuse existing graph explorer if suitable; otherwise deliver a lightweight graph page for the POC. | End user can navigate from an answer to the supporting graph path and images. | Must
FR-12 | Fast response and caching | Cache processed manuals, graph builds, prompt/context bundles, common query results, and image/diagram references where appropriate. | Caching must not prevent updated validations from being reflected after rebuild. | Repeated questions respond faster and show when cached sources were used. | Should
FR-13 | Security and role management | Demonstrate authentication, role-based access, document-level permissions, secure handling of documents/assets, audit logging, and encryption/IAM/SSO alignment. | If the existing platform has security controls, integrate with them; otherwise define the minimum POC control model and production upgrade path. | Roles can restrict manual access and graph/image visibility. | Must
FR-14 | Cloud-aligned delivery | Deliver in line with common cloud-platform patterns such as AWS-native or AWS-compatible storage, compute, databases, logging, monitoring, IAM, and deployment practices. | Production-grade scalability, enterprise hardening, billing, and multi-tenant administration should be delivered as platform-aligned service upgrades where required. | Technical documentation names the selected POC services and future upgrades. | Should

## Response Contract
Structured Tool Response Contract
Expected response fields so the existing system can show business-friendly graph flow, evidence, images, and confidence.
Field | Type / Format | Purpose | Example | Required
answer | Text | Concise natural-language answer to the user’s question. | The likely cause is a loose connector at terminal X3. | Yes
ordered_steps | Array of step objects | Exact procedure in the correct order, including warnings, prerequisites, tools, and parts. | Step 1: Isolate power. Step 2: Remove cover… | Yes for procedures
business_graph_path | Array / path string | Business-friendly trace showing how the answer is grounded in the graph. | Product → Fault → Component → Wiring Diagram → Procedure → Step 1…n | Yes
evidence | Array | Source pages, sections, snippets, diagram IDs, and graph node references. | Manual p.12, Fig. 4, Node: Connector X3 | Yes
image_references | Array | Stored diagrams/images linked to graph node popups and answer evidence. | image_id=wire_diag_004, page=12 | Yes when relevant
confidence | Score + label | Show answer reliability and protect users from low-confidence outputs. | 0.87 / High | Yes
assumptions | Array | State assumptions where manual evidence is incomplete or ambiguous. | Assumes Model A revision 2. | Should
review_needed | Boolean + reason | Flag low-confidence or safety-critical answers for review. | true: conflicting diagram labels | Yes
cache_metadata | Object | Show cache source, cache freshness, and rebuild status. | graph_cache_v7, refreshed 2026-06-17 | Should
security_context | Object | Carry user role/document access context into response and UI rendering. | role=technician, manual_access=true | Should

## Success Criteria
Success Criteria
Accuracy, confidence, traceability, speed, and security criteria for the POC.
ID | Criterion | Expected Outcome | Acceptance Test | Priority
SC-01 | Complex manual accuracy | Correctly answer complex questions from technical manuals containing wiring diagrams, images, tables, and step-by-step procedures. | Run agreed sample questions against sample manuals and review against expert answer key. | Must
SC-02 | Exact ordered steps | For “how do I…” questions, return exact steps in the correct order with no skipped safety warnings, prerequisites, parts, or tools. | Compare returned step sequence to source procedure and expert review. | Must
SC-03 | Diagram understanding | Demonstrate understanding of technical diagrams by connecting diagram objects to components, source text, procedures, and graph relationships. | Ask a diagram-dependent question and verify the returned component/connection path. | Must
SC-04 | Business-friendly graph trace | Each answer shows a logical graph flow that business users can understand. | Answer includes a path such as Product → Fault → Component → Diagram → Procedure → Step. | Must
SC-05 | Image evidence and popups | Stored images/wiring diagrams can be opened from graph nodes and answer evidence for later referencing. | Graph page shows relevant image popup from a cited source page. | Must
SC-06 | Confidence and uncertainty | End users can see why an answer is trustworthy through confidence indicators, evidence links, and review flags where confidence is low. | Low-confidence sample returns a warning or review-needed flag instead of overconfident answer. | Must
SC-07 | Fast practical response | Repeated questions and previously processed manuals respond quickly using caching where appropriate. | Repeated query uses cached graph/context and responds within a practical target agreed for the POC. | Should
SC-08 | Security and roles | Role-based access, auditability, secure document handling, and image/graph visibility controls are demonstrable. | User with restricted role cannot view unauthorised manual, graph node, or image asset. | Must
SC-09 | Upgrade clarity | Production gaps are clearly identified as platform-aligned upgrades rather than hidden inside the POC. | Documentation lists production-scale, security, multi-tenant, billing, and document-format upgrades. | Should

## Indicative Flow 1
Indicative Diagram 1 — Original Document Graph Pipeline
Original flow showing ingestion, extraction, validation, graph build, and graph/vector DB storage.
Indicative only — based on the original uploaded draw.io diagram. It is not intended to be final implementation architecture.

## Indicative Flow 2
Indicative Diagram 2 — Original Query and UI Flow
Original flow showing UI, knowledge graph, graph/vector DB, query flow, context/prompt store, response handling, cache, and user management.
Indicative only — based on the original uploaded draw.io diagram. It is not intended to be final implementation architecture.

## Source Notes
Source Notes
Traceability and assumptions used for this Excel export.
Item | Note | Source / Reference | Status
Original diagrams | The diagram sheets are reproduced from the original uploaded draw.io file and labelled as indicative logical flows. | DocumentGraphPipeline.drawio | Included
HTML brief | The Excel workbook reflects the latest requirements discussed: existing-system supplement, business schema, graph-linked responses, image popups, caching, security, and role management. | DocumentGraphPipeline_POC_Requirements.html | Converted
Scope assumption | This is a POC brief. Production scalability, enterprise hardening, advanced tenant administration, billing, and exhaustive document support should be treated as upgrade paths unless agreed. | User direction | Included
Platform assumption | Delivery should align with common cloud-platform patterns such as AWS-native or AWS-compatible storage, compute, databases, IAM, logging, monitoring, and deployment practices. | User direction | Included